## Cover Page
TEST PLAN - OpenCart E-Commerce
Manual Testing Project
| Document ID | TP-OC-001
| Version | 1
| Date | 2026-03-01
| Prepared By | Ayush
| Project Name | OpenCart E-Commerce Testing
| Application URL | https://demo.opencart.com
| Testing Type | Manual Black-Box Testing
| Status | Draft

## Objective & Scope
OBJECTIVE & SCOPE
1. OBJECTIVE
To verify that all main features of the website are working correctly and users can complete their tasks without any issues.
2. SCOPE – IN SCOPE
Module | Details
User Registration & Login | Positive & negative test cases
Product Search & Filtering | Valid/invalid keywords, category filters
Shopping Cart | Add, update quantity, remove items
Checkout Process | Guest checkout & registered user checkout
Order History & My Account | View orders, account details
Wishlist | Add and remove products
Admin Panel (Basic) | Login, product listing view
UI / Usability | Navigation, broken links, responsiveness
3. SCOPE – OUT OF SCOPE
Payment Gateway transactions
Performance testing
System testing
Automated testing
Security testing

## Test Items
TEST ITEMS – OPENCART MODULES
# | Module | Feature / URL | Test Priority
1 | Registration |  | High
2 | Login/Logout |  | High
3 | Product Search |  | High
4 | Product Details |  | Medium
5 | Shopping Cart |  | High
6 | Checkout |  | High
7 | Order History |  | Medium
8 | Wishlist |  | Medium
9 | My Account |  | Medium
10 | Admin – Login |  | High
11 | Admin – Products |  | Low
12 | Navigation & UI |  | Medium
Note: URL field is left blank as it is generated by the application.

## Test Approach
TEST APPROACH & STRATEGY
Testing Type | Manual functional testing (Black-box)
Testing Level | System Testing & Integration Testing
Test Design Techniques | Using simple methods like equivalence partitioning, boundary value analysis, and some exploratory testing
Test Execution | Test cases will be executed manually step by step
Bug Tracking | Bugs will be recorded in Excel sheet (Jira can be used)
Test Documentation | Test Scenarios → Test Cases → Bug Report → RTM → Summary Report
Browser Coverage | Testing will be done on Chrome mainly, and also checked on Firefox and Edge
Environment | demo.opencart.com
Test Data | new email IDs, dummy addresses
Regression Approach | Re-test all High priority test cases after any bug fix
Note: Test approach and testing strategy are defined by the Test Manager or QA Lead.

## Entry&Exit
ENTRY & EXIT CRITERIA
ENTRY CRITERIA (Testing can START when…)
Application is available for testing
Test cases are prepared
Test environment is ready
Test data (accounts, emails, addresses) is ready
Bug report template / sheet is prepared
EXIT CRITERIA (Testing can STOP when…)
Most test cases are executed
Critical and high bugs are fixed or approved
No new critical bugs found
Test summary is completed
RTM is updated

## Environment
TEST ENVIRONMENT
Application Name | OpenCart E-Commerce Demo
Application URL | https://demo.opencart.com
Admin URL | https://demo.opencart.com/admin
Operating System | Windows 10 / Windows 11
Primary Browser | Google Chrome (latest version)
Secondary Browsers | Microsoft Edge, Firebox
Screen Resolution | 1920×1080 (Full HD)
Internet Connection | Stable broadband required
Test Tools | Excel (test cases & bug report)
Bug Tracking | Excel Bug Report Sheet / Jira
Screenshot Tool | Snipping Tool / Lightshot
Local Setup (Backup) | XAMPP + OpenCart local install if demo site is down

## Schedule
TEST SCHEDULE & MILESTONES
# | Phase / Activity | Duration | Deliverable
1 | Test Planning | Day 1 – Day 2 | Test Plan
2 | Requirement Analysis | Day 2 – Day 3 | Requirement Notes
3 | Test Scenario Writing | Day 3 – Day 4 | Test Scenarios Sheet
4 | Test Case Writing | Day 4 – Day 6 | Test Cases Sheet
5 | Test Environment Setup | Day 6 | Environment Ready
6 | Smoke Testing | Day 7 | Smoke Test Result
7 | Functional Testing | Day 7 – Day 10 | Executed Test Cases
8 | Integration Testing | Day 8 – Day 10 | Integration Results
9 | Exploratory Testing | Day 9 – Day 11 | Observation Notes
10 | Bug Reporting & Tracking | Day 7 – Day 12 | Bug Report Sheet
11 | Regression Testing | Day 12 – Day 13 | Regression Result
12 | User Acceptance Testing (Basic Level) | Day 13 | UAT Notes
13 | RTM Update | Day 13 | RTM Sheet
14 | Test Summary Report | Day 14 | Test Summary
Note: This schedule covers all testing activities and includes some advanced methods like integration and exploratory testing to make the process more effective.

## Roles
ROLES & RESPONSIBILITIES
Role | Name | Responsibilities
Test Lead / Planner | [Your Name] | Prepare test plan, define scope, review test cases
Manual Tester | [Your Name] | Write test scenarios & cases, execute tests
Bug Reporter | [Your Name] | Log bugs with severity, priority, and steps
Document Owner | [Your Name] | Maintain test documents and update files

## Risks
RISKS & MITIGATIONS
Risk | Severity | Mitigation Plan
Demo site is slow or not working | High | Use local setup as backup
Test data gets reset | High | Create test data again when needed
Requirements are not clear | Medium | Use basic testing and explore the application
Limited time | Medium | Focus on important test cases first
Browser issues | Low | Test mainly on Chrome and check others if possible
Environment difference | Medium | Note environment details during testing
Missing or duplicate test cases | Low | Review test cases and use RTM