## RTM
REQUIREMENTS TRACEABILITY MATRIX — OpenCart Manual Testing
Project: demo.opencart.com ¦ Tester: Ayush ¦ Cycle: 1 ¦ Type: Manual Black-Box Testing ¦ Total TCs: 40 ¦ Pass: 37 ¦ Fail: 3
Req ID | Module | Requirement | Scenario ID | Test Scenario | Test Case ID | Test Case Title | Priority | Test Type | Status
REQ-001 | Homepage | System shall display homepage with navigation and banners | SC_001 | Verify that homepage opens successfully in browser | TC_001 | Verify homepage loads successfully in browser | High | Functional | Pass
REQ-001 | Homepage | System shall display homepage with navigation and banners | SC_001 | Verify that homepage opens successfully in browser | TC_002 | Verify page title is correct on homepage | Medium | Functional | Pass
REQ-001 | Homepage | System shall display homepage with navigation and banners | SC_002 | Verify top navigation menu is visible with all category links | TC_003 | Verify top navigation menu is visible | High | Functional | Pass
REQ-001 | Homepage | System shall display homepage with navigation and banners | SC_002 | Verify top navigation menu is visible with all category links | TC_004 | Verify all category links are clickable in nav menu | High | Functional | Pass
REQ-001 | Homepage | System shall display homepage with navigation and banners | SC_003 | Verify banner images are loading without any broken image | TC_005 | Verify banner images load without broken images | Medium | UI | Pass
REQ-001 | Homepage | System shall display homepage with navigation and banners | SC_004 | Verify clicking on a category from menu goes to correct page | TC_006 | Verify clicking category from menu navigates correctly | High | Functional | Pass
REQ-002 | Registration | System shall allow new users to register with valid details | SC_005 | Verify user can register with all valid details | TC_007 | Verify registration with all valid details | High | Functional | Pass
REQ-002 | Registration | System shall allow new users to register with valid details | SC_006 | Verify error shown when firstname field is left blank | TC_008 | Verify error shown when First Name is blank | High | Negative | Pass
REQ-002 | Registration | System shall allow new users to register with valid details | SC_006 | Verify error shown when firstname field is left blank | TC_009 | Verify error shown when Last Name is blank | High | Negative | Pass
REQ-002 | Registration | System shall allow new users to register with valid details | SC_007 | Verify error shown when email field is left blank | TC_010 | Verify error shown when Email field is blank | High | Negative | Pass
REQ-002 | Registration | System shall allow new users to register with valid details | SC_008 | Verify system accepts invalid email format like 'abc@' | TC_011 | Verify invalid email format 'abc@' is rejected | Medium | Negative | Fail
REQ-002 | Registration | System shall allow new users to register with valid details | SC_009 | Verify password and confirm password mismatch shows error | TC_012 | Verify password mismatch shows error | High | Negative | Pass
REQ-002 | Registration | System shall allow new users to register with valid details | SC_009 | Verify password and confirm password mismatch shows error | TC_013 | Verify strong password is accepted | Medium | Functional | Pass
REQ-003 | Login | System shall allow registered users to login securely | SC_010 | Verify user can login with valid email and password | TC_014 | Verify login with valid email and password | High | Functional | Pass
REQ-003 | Login | System shall allow registered users to login securely | SC_011 | Verify error message shown for wrong password | TC_015 | Verify error shown for wrong password | High | Negative | Pass
REQ-003 | Login | System shall allow registered users to login securely | SC_011 | Verify error message shown for wrong password | TC_016 | Verify error shown for wrong email | High | Negative | Pass
REQ-003 | Login | System shall allow registered users to login securely | SC_012 | Verify login fails when email and password fields are empty | TC_017 | Verify login fails when both fields are empty | High | Negative | Pass
REQ-003 | Login | System shall allow registered users to login securely | SC_013 | Verify Forgot Password link is present and clickable | TC_018 | Verify Forgot Password link is present | Medium | Functional | Pass
REQ-003 | Login | System shall allow registered users to login securely | SC_013 | Verify Forgot Password link is present and clickable | TC_019 | Verify Forgot Password link navigates to reset page | Medium | Functional | Pass
REQ-004 | Logout | System shall allow users to logout securely | SC_014 | Verify user can logout from My Account menu | TC_020 | Verify user can logout from My Account menu | High | Functional | Pass
REQ-004 | Logout | System shall allow users to logout securely | SC_014 | Verify user can logout from My Account menu | TC_021 | Verify accessing account page after logout redirects to login | High | Functional | Pass
REQ-005 | Search | System shall allow users to search products by keyword | SC_015 | Verify search returns results for valid keyword like MacBook | TC_022 | Verify search returns results for valid keyword 'MacBook' | High | Functional | Pass
REQ-005 | Search | System shall allow users to search products by keyword | SC_015 | Verify search returns results for valid keyword like MacBook | TC_025 | Verify search is case-insensitive | Low | Functional | Pass
REQ-005 | Search | System shall allow users to search products by keyword | SC_016 | Verify message shown when searched keyword has no results | TC_023 | Verify no results message for unknown keyword | High | Negative | Pass
REQ-005 | Search | System shall allow users to search products by keyword | SC_017 | Verify searching with empty field shows warning message | TC_024 | Verify warning shown when search field is empty | Medium | Negative | Fail
REQ-006 | Product | System shall display complete product details on product page | SC_018 | Verify product detail page opens on clicking a product | TC_026 | Verify product detail page opens on clicking a product | High | Functional | Pass
REQ-006 | Product | System shall display complete product details on product page | SC_019 | Verify product name price and image visible on detail page | TC_027 | Verify product name is visible on detail page | High | Functional | Pass
REQ-006 | Product | System shall display complete product details on product page | SC_019 | Verify product name price and image visible on detail page | TC_028 | Verify product price is visible on detail page | High | Functional | Pass
REQ-006 | Product | System shall display complete product details on product page | SC_019 | Verify product name price and image visible on detail page | TC_029 | Verify product image is visible on detail page | High | Functional | Pass
REQ-006 | Product | System shall display complete product details on product page | SC_020 | Verify user can change quantity and add product to cart | TC_030 | Verify user can change quantity and add to cart | High | Functional | Pass
REQ-006 | Product | System shall display complete product details on product page | SC_021 | Verify entering 0 in quantity field before adding to cart | TC_031 | Verify entering quantity 0 shows error | Medium | Negative | Fail
REQ-007 | Shopping Cart | System shall allow users to manage their shopping cart | SC_022 | Verify product gets added to cart on clicking Add to Cart | TC_032 | Verify product is added to cart on clicking Add to Cart | High | Functional | Pass
REQ-007 | Shopping Cart | System shall allow users to manage their shopping cart | SC_023 | Verify user can remove a product from the cart | TC_033 | Verify user can remove a product from the cart | High | Functional | Pass
REQ-007 | Shopping Cart | System shall allow users to manage their shopping cart | SC_024 | Verify cart total is updating when quantity is changed | TC_034 | Verify cart total updates when quantity is changed | High | Functional | Pass
REQ-007 | Shopping Cart | System shall allow users to manage their shopping cart | SC_024 | Verify cart total is updating when quantity is changed | TC_035 | Verify cart is empty message when all products removed | Medium | Functional | Pass
REQ-008 | Checkout | System shall allow users to complete checkout successfully | SC_025 | Verify user can complete checkout as a guest user | TC_036 | Verify user can complete checkout as guest | High | Functional | Pass
REQ-008 | Checkout | System shall allow users to complete checkout successfully | SC_025 | Verify user can complete checkout as a guest user | TC_038 | Verify order confirmation email mention on success page | Medium | Functional | Pass
REQ-008 | Checkout | System shall allow users to complete checkout successfully | SC_026 | Verify error shown when billing address fields are empty | TC_037 | Verify error shown when billing address fields are empty | High | Negative | Pass
REQ-009 | My Account | System shall allow users to manage their account details | SC_027 | Verify user can update their name from Edit Account page | TC_039 | Verify user can update name from Edit Account page | Medium | Functional | Pass
REQ-009 | My Account | System shall allow users to manage their account details | SC_028 | Verify order history is visible under My Account section | TC_040 | Verify order history is visible under My Account | Medium | Functional | Pass

## Summary
RTM SUMMARY DASHBOARD — OpenCart Manual Testing
Module | Test Cases | Pass | Fail | Pass Rate | Status
Homepage | 6 | 6 | 0 | 100.0% | Pass
Registration | 7 | 6 | 1 | 85.7% | Pass with Defect
Login | 6 | 6 | 0 | 100.0% | Pass
Logout | 2 | 2 | 0 | 100.0% | Pass
Search | 4 | 3 | 1 | 75.0% | Pass with Defect
Product | 6 | 5 | 1 | 83.3% | Pass with Defect
Shopping Cart | 4 | 4 | 0 | 100.0% | Pass
Checkout | 3 | 3 | 0 | 100.0% | Pass
My Account | 2 | 2 | 0 | 100.0% | Pass
TOTAL | 40 | 37 | 3 | 92.5% | Pass with Defects