## Cover
OpenCart Demo ¦ E-Commerce Testing Project
PROJECT INFORMATION
Project Name |  | E-Commerce Testing Project
Application |  | OpenCart Demo Website
URL |  | demo.opencart.com
Test Cycle |  | Cycle 1
Test Type |  | Functional Testing
Environment |  | Chrome Browser / Windows
Prepared By |  | [YOUR NAME]
Reviewed By |  | [REVIEWER NAME]
Report Date |  | [DD-MMM-YYYY]
Start Date |  | [DD-MMM-YYYY]
End Date |  | [DD-MMM-YYYY]
MODULES TESTED
Homepage |  | ✅ Covered
Registration |  | ✅ Covered
Login |  | ✅ Covered
Logout |  | ✅ Covered
Search |  | ✅ Covered
Product |  | ✅ Covered
Shopping Cart |  | ✅ Covered
Checkout |  | ✅ Covered
My Account |  | ✅ Covered

## Summary
Executive Summary ¦ OpenCart Demo Testing
Cycle 1 ¦ Functional Testing ¦ demo.opencart.com
PASS RATE : 92.5% ¦ 3 Bugs Found ¦ Overall Status : PASS WITH DEFECTS
MODULE-WISE TEST RESULTS
Module | Test Cases | Pass | Fail | Pass Rate | Status
Homepage | 6 | 6 | 0 | 100.0% | Pass
Registration | 7 | 6 | 1 | 85.7% | Pass with Defect
Login | 6 | 6 | 0 | 100.0% | Pass
Logout | 2 | 2 | 0 | 100.0% | Pass
Search | 4 | 3 | 1 | 75.0% | Pass with Defect
Product | 6 | 5 | 1 | 83.3% | Pass with Defect
Shopping Cart | 4 | 4 | 0 | 100.0% | Pass
Checkout | 3 | 3 | 0 | 100.0% | Pass
My Account | 2 | 2 | 0 | 100.0% | Pass
TOTAL | 40 | 37 | 3 | 92.5% | Pass with Defects

## Sign-off
Test Sign-Off
OpenCart Demo ¦ E-Commerce Testing Project ¦ Cycle 1
OVERALL VERDICT : PASS WITH DEFECTS
FINAL TEST SUMMARY
Total Test Scenarios |  | 28
Total Test Cases |  | 40
Test Cases Passed |  | 37
Test Cases Failed |  | 3
Overall Pass Rate |  | 92.5%
Bugs Found |  | 3
Critical Bugs |  | 1
Bugs Status |  | All Open — Fix Required
Release Recommendation |  | NOT recommended for production until bugs are fixed
APPROVAL & SIGN-OFF
Role | Name | Signature | Date
QA Tester | [YOUR NAME] | ___ | [Date]
QA Lead | [QA LEAD NAME] | ___ | [Date]
Project Manager | [PM NAME] | ___ | [Date]